## Event outline_event checklist
Event outline / checklist
Item | Information | Notes | Owner | Due Date | Status | Comments
Name
Goal / Objective
Description
Date
Time
Budget
Music / Live band / DJ
Ticket Price
Capacity goal
Sponsors / Partners / vendors
Culinary
Beverage
Ticketing setup
Giveaway / Takeaway items
Charitable Component
Collateral
PR support
Marketing

## Event pro forma
Event pro forma - Summertime BBQ
Venue:
Event:
Date:
Revenue | breakeven |  |  | good case |  |  | best case
| Tickets | Price | Revenue | Tickets | Price | Revenue | Tickets | Price | Revenue | Comments / Assumptions
GA | 120 | 0 | 0 | 150 | 0 | 0 | 180 | 0 | 0 | General public / general admission
VIP - Sales clients / Hotel guests | 5 | 0 | 0 | 10 | 0 | 0 | 15 | 0 | 0 | VIP angle to capture Sales clients
VIP - PR guestlist | 15 | 0 | 0 | 20 | 0 | 0 | 25 | 0 | 0 | Influencers to be shortlisted, PR to drive this
F&B Revenue | - | 18 | 2520 | - | 22 | 3960 | - | 26 | 5720 | Average Incremental F&B spend per patron
Sub total | 140 |  | 2520 | 180 |  | 3960 | 220 |  | 5720
Total Revenue |  |  | 2520 |  |  | 3960 |  |  | 5720
Charitable contribution |  |  | 0 |  |  | 47.25 |  |  | 78.75 | (For consideration)
Expenses
Operating Expenses
Cost of Goods Sold |  |  | 504 |  |  | 792 |  |  | 1144 | 20% COGS (blended, ~90% Beverage sales)
Entertainment |  |  | 1100 |  |  | 1100 |  |  | 1100 | Initial discussion - Craig Dash, Cosmo Baker
Production |  |  | 0 |  |  | 0 |  |  | 0
Promoter |  |  | 0 |  |  | 0 |  |  | 0
Transportation |  |  | 0 |  |  | 0 |  |  | 0
Rooms |  |  | 0 |  |  | 0 |  |  | 0
Décor / Decorations |  |  | 500 |  |  | 500 |  |  | 500 | Décor, large format games (Connect Four, Cornhole)
Photographer / Videographer |  |  | 0 |  |  | 0 |  |  | 0
VIP Invitation |  |  | 0 |  |  | 0 |  |  | 0
VIP Giveaway |  |  | 0 |  |  | 0 |  |  | 0
Incremental Labor |  |  | 0 |  |  | 0 |  |  | 0
Marketing / Printing / Signage |  |  | 400 |  |  | 400 |  |  | 400 | Marketing, printing, signage, digial ad campaign
Contingency @ 10% |  |  | 250.4 |  |  | 279.2 |  |  | 314.4
Sponsorship (contra expense)
Sponsorship |  |  | -1000 |  |  | -1000 |  |  | -1000 | Marketing, printing, entertainment, spend/swipe, etc.
Total Costs |  |  | 1754.4 |  |  | 2071.2 |  |  | 2458.4
Projected GOP |  |  | 765.6 |  |  | 1888.8 |  |  | 3261.6
Profit Margin |  |  | 30.38% |  |  | 47.7% |  |  | 57.02%
Charitable contribution |  |  | 0 |  |  | 47.25 |  |  | 78.75
Raffle |  |  | 0 |  |  | 0 |  |  | 0
Total charitable contribution |  |  | 0 |  |  | 47.25 |  |  | 78.75
ESTIMATED NOI |  |  | 765.6 |  |  | 1841.55 |  |  | 3182.85
Profit Margin |  |  | 30.38% |  |  | 46.5% |  |  | 55.64%

## Event timeline
June | [6 empty] | July | [30 empty] | August
24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Brief submitted | [13 empty] | First creative proof | [6 empty] | Creative finalized |  |  | Event to go live | [27 empty] | 2nd Email blast |  | Event date
Action Items
Marketing collateral
June 24 - Creative brief submitted
July 8 - First proof of the creative for review
July 15 - All marketing collateral to be finalized
Flyers ordered, Email blast, Social tile, Facebook / Instagam Ad, etc.
Event Announcement
Thursday, July 18
Initial Email blast sent
SevenRooms event live / 'tickets' on sale (ability for guests to RSVP)
Website updated with event graphic
On-going initiatives
Flyers distributed on property - Check presenters, Red Owl
July 18 - August 17
Facebook/Instagram ad campaign - PPC to SevenRooms event page
Finalize budget, determine optimal days to run this
~Friday, August 8 - Saturday, August 17 - Social Media team to advise on specifics
Email blast schedule
1st blast - Thursday, July 18
2nd blast - Thursday, August 15
Event date
Saturday, August 17

## Marketing outline
Marketing outline
3 MONTHS out | 1 MONTH out
Discuss the idea, include DO | Restaurant and Hotel Staff Training and Tasting
Outline the event pro forma | Facebook and Instagram Post
Reach out to Restaurant Marketing team for strategy support, if needed | Partner Social Media Post
Schedule and Plan the event | Hotel Social Media Post
- Outline theme / content and reserve dates at least 2 months out | Email Marketing
- Reach out if planning to include any partners | Wi-Fi Landing Page Message
Connect with PR team | A-Frame Outdoor Signage
Reach out to hotel team to set up Dynamic Package (if applicable) | Off-Site Event Participation
Local / National Partnership Outreach | Staff Sales Competition
Collateral Request Submission: Menu / Check Presenter / Postcard / Poster / Bounce-back / In-Room
WEEK BEFORE
2 MONTHS out | Facebook and Instagram Post
Locu Digital Menu Submission | Hotel Social Media Post
Sales Team Collaboration: Discuss Private Dining Opportunities and Packages | Email Marketing
Coordinate Photography Needs | Menus / Collateral Needed Day Of - Sent to Printer
Restaurant and Hotel Website Listing Request | Neighborhood & Concierge Outreach
Facebook and Instagram Post
Google My Business Post | DAY BEFORE
Email Marketing | Facebook and Instagram Post
Collateral Sent to Printer | Wine Hour Attendance
Collateral Distribution
DAY OF
Photo / Video shoot (Schedule photographer to capture the experience)
KIPSU Message (if space is still available)
Wine Hour Attendance
Influencer Account Takeover